## Sheet1
Lofthus frukt og saft |  |  | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4
Tasks | Start date | End date | 2019-02-25 | 2019-02-26 | 2019-02-27 | 2019-02-28 | 2019-03-01 | 2019-03-04 | 2019-03-05 | 2019-03-06 | 2019-03-07 | 2019-03-08 | 2019-03-11 | 2019-03-12 | 2019-03-13 | 2019-03-14 | 2019-03-15 | 2019-03-18 | 2019-03-19 | 2019-03-20 | 2019-03-21 | 2019-03-22
Project management and customer contact | 2019-02-25 | 2019-03-22 | Project manager |  |  |  |  | Project manager |  |  |  |  | Project manager |  |  |  |  | Project manager
Initial meeting with client | 2019-02-25 | 2019-02-25 | Project Manager, Front-End Developer
Project planning, identify goals and needs | 2019-02-25 | 2019-02-27 | Project manager, Front-End developer, Designer
Research | 2019-02-26 | 2019-02-28 |  | Front-End developer, Designer
Biweekly informational meeting with client | 2019-03-01 | 2019-03-01 |  |  |  |  | Project Manager, Front-End developer
Strategic and content planning | 2019-03-01 | 2019-03-05 |  |  |  |  | Project manager, Front-End developer, Designer | Project manager, Front-End developer, Designer
Create a style tile, sketches and wireframe | 2019-03-06 | 2019-03-08 | [7 empty] | Front-end developer, Designer
Text content development | 2019-03-07 | 2019-03-11 | [8 empty] | Copywriter |  | Copywriter
Photoshoot (of products and employee) | 2019-03-07 | 2019-03-12 | [8 empty] | Photographer |  | Photographer
Edit photos | 2019-03-13 | 1900-01-14 00:43 | [12 empty] | Photographer
Coding, integration and build site | 2019-03-11 | 2019-03-19 | [10 empty] | Front-End developer |  |  |  |  | Front-End developer, Back-End developer
UX/UI Planning and testing | 2019-03-12 | 2019-03-13 | [11 empty] | Front-End developer, Designer
Biweekly meeting with client | 2019-03-15 | 2019-03-15 | [14 empty] | Project Manager, Front-End developer
UX/UI testing | 2019-03-18 | 2019-03-18 | [15 empty] | Front-End developer, Designer
Browser and cross platform testing | 2019-03-19 | 2019-03-20 | [16 empty] | Front-End developer, Back-End developer
Validating | 2019-03-21 | 2019-03-21 | [18 empty] | Back-End developer
Final meeting with client | 2019-03-21 | 2019-03-21 | [18 empty] | Project Manager Front-End developer
Launch site | 2019-03-22 | 2019-03-22 | [19 empty] | Project manager, Front-End developer, Designer
Launch site
Project manager,
Front-End developer,
Designer
Project manager,
Front-End developer,
Designer
Project manager,
Front-End developer,
Designer
Project manager,
Front-End developer,
Designer
22-03
22-03
01-03
05-03
25-02
27-02
Strategic and content planning
Project planning, identify goals and needs